## RentYourExpert Scrum
Scrum Project Management
[10 empty] | SPRINTS | SPRINT 1
SPRINT 2
SPRINT 3
SPRINT 4
SPRINT 5
| WORK BREAKDOWN STRUCTURE | TASK TITLE | TASK OWNER | AMOUNT OF WORK IN HOURS |  |  | SPRINT | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
|  |  |  | ESTIMATE | COMPLETED | REMAINING | [5 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
| 1 | Initial Structure of the project |  | 79 | 79 | 0 |  |  |  |  | 100%
| 1.1 | Build Database | Andrea | 10 | 10 | 0 |  | 2023-01-17 | 2023-01-22 | 6 | 100% | bar: WEEK 1 T to WEEK 2 M; WEEK 2 R to WEEK 2 F
| 1,1.2 | Containerization of the database | Andrea | 8 | 8 | 0 |  | 2023-01-22 | 2023-01-27 | 6 | 100%
| 1,2 | Add catalogue microservice | Lorenzo | 10 | 10 | 0 |  | 2023-01-18 | 2023-01-25 | 8 | 100% | bar: WEEK 1 W to WEEK 2 F
| 1,3 | Connect DB and microservice | Andrea | 9 | 9 | 0 |  | 2023-01-27 | 2023-02-02 | 7 | 100% | bar: WEEK 2 M to WEEK 3 R
| 1,4 | Build initial frontend | Eleonora | 9 | 9 | 0 |  | 2023-01-19 | 2023-01-25 | 7 | 100% | bar: WEEK 1 R to WEEK 2 F
| 1,4.1 | React Setup | Eleonora | 15 | 15 | 0 |  | 2023-01-25 | 2023-02-03 | 10 | 100% | bar: WEEK 2 M to WEEK 3 F
| 1,5 | Catalogue microservice on React | Lorenzo | 12 | 12 | 0 |  | 2023-02-01 | 2023-02-08 | 8 | 100% | bar: WEEK 3 W to WEEK 4 W
| 1,6 | Setup login microservice | Lorenzo | 6 | 6 | 0 |  | 2023-02-08 | 2023-02-11 | 4 | 100% | bar: WEEK 4 W to WEEK 5 F
| 2 | Develop the body of the e-commerce |  | 71 | 71 | 0 |  |  |  |  | 100%
| 2,1 | Add management microservice | Andrea | 17 | 17 | 0 |  | 2023-02-08 | 2023-02-19 | 12 | 100% | bar: WEEK 4 W to WEEK 5 F
| 2,2 | Add reviews microservice | Lorenzo | 9 | 9 | 0 |  | 2023-02-11 | 2023-02-17 | 7 | 100%
| 2,3 | Add customer login microservice | Lorenzo | 15 | 15 | 0 |  | 2023-02-17 | 2023-02-23 | 7 | 100% | bar: WEEK 5 M to WEEK 6 R
| 2,3.1 | Customer login microservice on React | Eleonora | 10 | 10 | 0 |  | 2023-02-23 | 2023-02-28 | 6 | 100% | bar: WEEK 6 R to WEEK 7 T
| 2,4 | Build homepage | Eleonora | 7 | 7 | 0 |  | 2023-03-01 | 2023-03-05 | 5 | 100% | bar: WEEK 7 W to WEEK 8 F
| 2,5 | Add admin login in management ms | Andrea | 6 | 6 | 0 |  | 2023-02-22 | 2023-02-28 | 7 | 100% | bar: WEEK 6 W to WEEK 7 T
| 2,6 | Add worker login microservice | Lorenzo | 3 | 3 | 0 |  | 2023-02-25 | 2023-02-28 | 4 | 100% | bar: WEEK 6 F to WEEK 7 T
| 2,7 | Management microservice frontend | Eleonora | 4 | 4 | 0 |  | 2023-03-05 | 2023-03-08 | 4 | 100% | bar: WEEK 7 F to WEEK 8 F
| 3 | Fixing/Completion steps |  | 41 | 41 | 0 |  |  |  |  | 100%
| 3,1 | Completion of the database | Andrea | 5 | 5 | 0 |  | 2023-03-03 | 2023-03-07 | 5 | 100% | bar: WEEK 7 F to WEEK 8 F
| 3.2 | Add navigate to the customer login | Lorenzo | 3 | 3 | 0 |  | 2023-03-07 | 2023-03-10 | 4 | 100%
| 3,3 | User profile frontend | Eleonora | 6 | 6 | 0 |  | 2023-03-08 | 2023-03-13 | 6 | 100% | bar: WEEK 8 M to WEEK 9 M
| 3,4 | Add request microservice | Andrea | 8 | 8 | 0 |  | 2023-03-11 | 2023-03-16 | 6 | 100% | bar: WEEK 8 M to WEEK 9 R
| 3,5 | Add q&a microservice | Lorenzo | 4 | 4 | 0 |  | 2023-03-11 | 2023-03-13 | 3 | 100% | bar: WEEK 8 M to WEEK 9 M
| 3,6 | User profile frontend | Eleonora | 5 | 5 | 0 |  | 2023-03-13 | 2023-03-16 | 4 | 100% | bar: WEEK 8 M to WEEK 9 R
| 3,7 | Customer + Worker Request frontend | Eleonora | 7 | 7 | 0 |  | 2023-03-17 | 2023-03-21 | 5 | 100% | bar: WEEK 9 F to WEEK 10 T
| 3.8 | Add logout | Lorenzo | 3 | 3 | 0 |  | 2023-03-17 | 2023-03-20 | 4 | 100% | bar: WEEK 9 F to WEEK 10 M
|  |  |  | ESTIMATE | COMPLETED | REMAINING | DAYS | EST/DAYS
|  | BURNDOWN DATA | TOTAL HOURS | 191 | 191 | 0 | 60 | 3.1833 |  |  | DAY | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | TOTAL HOURS
[7 empty] | ^ Enter number of days |  |  |  | PLAN | 191 | 187.8167 | 184.6333 | 181.45 | 178.2667 | 175.0833 | 171.9 | 168.7167 | 165.5333 | 162.35 | 159.1667 | 155.9833 | 152.8 | 149.6167 | 146.4333 | 143.25 | 140.0667 | 136.8833 | 133.7 | 130.5167 | 127.3333 | 124.15 | 120.9667 | 117.7833 | 114.6 | 111.4167 | 108.2333 | 105.05 | 101.8667 | 98.6833 | 95.5 | 92.3167 | 89.1333 | 85.95 | 82.7667 | 79.5833 | 76.4 | 73.2167 | 70.0333 | 66.85 | 63.6667 | 60.4833 | 57.3 | 54.1167 | 50.9333 | 47.75 | 44.5667 | 41.3833 | 38.2 | 35.0167 | 31.8333 | 28.65 | 25.4667 | 22.2833 | 19.1 | 15.9167 | 12.7333 | 9.55 | 6.3667 | 3.1833
[11 empty] | ESTIMATE | 191 | 183 | 163 | 133 | 93 | 73 | 62 | 46 | 4 | -41 | -61 | -71 | -87 | -111 | -159 | -179 | -183 | -188 | -192 | -200 | -208 | -213 | -218 | -223 | -226 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -9592
[10 empty] | Enter hours completed per day ----> | HRS COMPLETED | WEEK 1 M: 8; WEEK 1 T: 20; WEEK 1 W: 30; WEEK 1 R: 40; WEEK 1 F: 20; WEEK 2 M: 11; WEEK 2 T: 16; WEEK 2 W: 42; WEEK 2 R: 45; WEEK 2 F: 20; WEEK 3 M: 10; WEEK 3 T: 16; WEEK 3 W: 24; WEEK 3 R: 48; WEEK 3 F: 20; WEEK 4 M: 4; WEEK 4 T: 5; WEEK 4 W: 4; WEEK 4 R: 8; WEEK 4 F: 8; WEEK 5 M: 5; WEEK 5 T: 5; WEEK 5 W: 5; WEEK 5 R: 3; WEEK 5 F: 2 | 419
[11 empty] | HRS REMAINING | 183 | 163 | 133 | 93 | 73 | 62 | 46 | 4 | -41 | -61 | -71 | -87 | -111 | -159 | -179 | -183 | -188 | -192 | -200 | -208 | -213 | -218 | -223 | -226 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -228 | -10011
CLICK HERE TO CREATE GANTT CHART TEMPLATES IN SMARTSHEET